## Lower material-Signel hydra
Risk Assessment/Management Form
Ref:
Section / Dept: civil Contractor :- |  |  |  | Activity: Risk Assessment for Lowering of Materials by single Hydra | Location / Area :-
Sl No. | Basic Job Steps | Potential Hazard | Consequence | Current control measure | Risk rating |  |  |  | Probability | Initial Risk | Additional control measure | Risk rating |  |  |  | Probability | Residual risk
[5 empty] | P | E | A | R |  |  |  | P | E | A | R
1 | Reaching the man to the work location by ladder | Slip of man | Get injury | Ladder must be inclined at an angle of 70º. | 1 | 0 | 0 | 0 | 2 | 2
Ladder must be secured by rope at the top and bottom
Ladder to be extended up to 1m.from the landing point
To follow the 'Wah'system
Life line to be provided above the head height for anchoring the safety belt
2 | Lowering of materials by hydra | Fall of materials | Get Injury/ Fatality | Only skilled &experienced work men deployed in the job with safety shoe ,hand gloves ,safety helmet and tested tools &tackles. Use guide rope during shifting of materials and always keep away from swing area.Daily tool box talk before starting of job by crew supervisor. | 1 | 0 | 0 | 1 | 3 | 6
|  | Failure of wire rope sling/D-shackle | Get Injury | All the wire rope sling & D-shackle visually checked . Tested sling are colour coaded by a specific colour .Daily tool box talk before starting of job by crew supervisor. | 2 | 0 | 0 | 1 | 2 | 4
|  | Hooking of material | Get injury | Skilled workmen shall be engaged for hooking of material.Hook of hydra must be provided with hook latchaily tool box talk before starting of job by crew supervisor. | 1 | 0 | 0 | 0 | 2 | 2
|  | Shifting of material | Get injury | People should maintain safe distance from the load while lifting and shifting.Guied rope to be fixed on both ends of the material.Communication with the hydra operator will be one to one talk and signal will be issued by the signal man | 1 | 0 | 0 | 0 | 3 | 3
Shifting area should be of suitable for approach
|  | Unhooking of material | Injury to person | People should not unhook the sling during tension. Only skilled person will remove the sling from the hook. | 2 | 0 | 0 | 0 | 2 | 4
|  | Toppling of Hydra due to excess loading | Injury / Fatality | Marking of SWL at different lifting hooks of hydra. Only Trained & experienced operator operate the hydra.Material above the safe working load mentioned at the lifting position shall not be lifted. | 2 | 0 | 0 | 0 | 2 | 4
| Prepared By |  |  | Approved By | [6 empty] | Reviewed By
| MR.S.ADHIKARY |  |  | MR.S.K.GOSWAMI | [6 empty] | SANJAY ACHARYA
| Prepared By |  |  | Approved By | [6 empty] | Reviwed By
| Contractor |  |  | Contractor
| Date |  |  | Date | [6 empty] | Date